SUPPORT FOR CHANGE INITIATIVE [SUFOCI]

**ACTION PLAN FOR AUGUST 2013**

**WORLDVIEW MISSION [WM] CHIKHWAWA DEVELOPMENT CENTER PROJECT MALAWI**

|  |  |  |  |
| --- | --- | --- | --- |
| *WEEK August* | ACTIVITIES | VENUE | RESPONSIBLE PEOPLE |
| 1 August | -meeting local leaders-gospel literature distribution-file work | -kabvalo-nchalo T/C-OFFICE | -FRANCIS-ISHMAEL-LOCAL LEADERS |
| 2 August | -WM CDC site verification-gospel literature distribution-file work | -KABVALO-DYERATU T/C-OFFICE | -DISTRICT COUNCIL-FRANCIS-ISHMAEL-PHOTOGRAPHER |
| 3 August | -WM CDC site dedication prayers-gospel literature distribution-file work | -KABVALO-THABWA T/C-OFFICE | -PASTOR NSONA-FRANCIS-ISHMAEL-PASTOR GETINALA |
| **4 August** | -local pastors meeting-visit to an HIV/AIDS support group-visit to kabvalo CBO-file work | -GUMBWA SCHOOL-KABVALO-KABALO-OFFICE | -LOCAL PASTORS-FRANCIS-CBO OFFICIALS-SUPPORT GROUP. |

**BUDGET PLAN**

* ***TRANSPORT =MWK30 ,000.00***
* ***COMMUNICATION=MWK10,000.00***
* ***PHOTOs=MWK6,000.000***
* ***FOOD&REFRESHMENTS =MWK 20,000.00***

**TOTAL :MWK66 ,000.00/US$170.00**

**COMPILED BY** :FRANCIS CHIPUKUNYA **POSITION** :PROJECT LEADER **SIGN :**SIGNED **DATE** :30-07-13

**APPROVED BY** :HELENE H.OORD **POSITION** :CHAIR &FOUNDER [WM**] SIGN**:……………..**DATE:**…………..